## Monthly Data
Month | Target Signups (500) | Target Signups (750) | Actual Signups | Cumulative Actual | % to Goal (500) | % to Goal (750) | Monthly Growth % | Early Bird Cutoff? | Notes | Cumulative Target (500) | Cumulative Target (750)
Oct 2025 | 25 | 40 |  | 0 | 0% | 0% | 0% |  |  | 0 | 0
Nov 2025 | 20 | 30 |  | 0 | 0% | 0% | 0% |  |  | 0 | 0
Dec 2025 | 12 | 20 |  | 0 | 0% | 0% | 0% |  |  | 0 | 0
Jan 2026 | 13 | 20 |  | 0 | 0% | 0% | 0% |  |  | 0 | 0
Feb 2026 | 50 | 75 |  | 0 | 0% | 0% | 0% |  |  | 0 | 0
Mar 2026 | 75 | 110 |  | 0 | 0% | 0% | 0% |  |  | 0 | 0
Apr 2026 | 100 | 150 |  | 0 | 0% | 0% | 0% | Yes |  | 0 | 0
May 2026 | 125 | 185 |  | 0 | 0% | 0% | 0% |  |  | 0 | 0
Jun 2026 | 100 | 150 |  | 0 | 0% | 0% | 0% |  |  | 0 | 0

## Channel Performance
Channel | Signups | % of Total | Cost ($) | Cost per Signup ($) | Notes
Bronte Runners |  | 0 |  | 0
Instagram |  | 0 |  | 0
Email |  | 0 |  | 0
Expos/Booths |  | 0 |  | 0
Partners/Clubs |  | 0 |  | 0
Other |  | 0 |  | 0
TOTAL | 0

## Milestones
Date | Event | Objective | Owner | Status
Oct 17–18, 2025 | Toronto Waterfront Marathon Expo | Collect 100 leads | Greg + Yasmin | Planned
Nov 9, 2025 | Run of Hope Weekend – Promo Ends | Convert leads to signups | Charles | Planned
Jan 15, 2026 | Winter Promo Push | Reach 100 total registrations | Greg | Planned
Mar 1, 2026 | Spring Registration Push | Hit 250 total registrations | Yasmin | Planned
May 15, 2026 | Early Bird 2 Cutoff | Hit 400 total registrations | Greg | Planned
Jun 21, 2026 | Race Day | 500–750 participants | All | Planned

## Dashboard
Bronte Harbour Classic 5K – KPI Dashboard
Core KPIs
Total Registrations (to-date) | 0
Progress to 500 Goal | 0%
Progress to 750 Stretch Goal | 0%
Average Monthly Signups (to-date) | 0
Channel Performance
Top Channel Signups (to-date) | 0
Total Channel-Attributed Signups | 0
Notes
• Enter monthly Actual Signups in the "Monthly Data" sheet; dashboard updates automatically. • Use "Channel Performance" to attribute signups and track acquisition costs. • Cumulative chart compares your progress to 500 (goal) and 750 (stretch) targets. • Update milestones as you complete promotions, expos, and partner pushes.